## Slide 1: Penfield Pavilion Status Report
January 20, 2015
Presented by:
Penfield Building Committee - James Bradley, Chair
Robert Bellitto, Vice Chair, Andrew Graceffa, Secretary
Ian Bass, Jane Nelson, Ken Jones, Ellery Plotkin, Richard Speciale
Kevin Chamberlain, DeStefano & Chamberlain

## Slide 2
Committee Charge
Site Protection
Research & Due Diligence, Considerations
Repair Options
Background
Recommended Design Detail
Bulkhead Improvements
Presentation Agenda

## Slide 3: Penfield Building Committee
Formed by Board of Selectmen in December 2013
Key Elements of Committee Charge
  Review and recommend options and manage the repair of the Penfield Pavilion.
  Be guided by engineering analysis, coastal and geotechnical engineering reports, FEMA standards, flood mitigation, technical reports.
  Be guided by public comment and neighborhood concerns.
  In evaluating options consider, minimizing ongoing maintenance, incorporating “green” initiatives and “time tested” design features.
  Maximize opportunities for FEMA reimbursement.
  Consider and integrate any flood mitigation measures.

## Slide 4: Tropical Storm Irene - 2011
  High winds/astronomical high tides;
  Storm surge but low wave energy

## Slide 5: Tropical Storm Irene - 2011
  Impact to the Pavilion
    Erosion of sands underneath the building
    Several footings undermined
    Front entrance porch settled

## Slide 6: Irene Restoration
  Restoration of the Pavilion Included:
    Underpinning performed
    Protective bulkhead designed and constructed
    Building structure repaired and reopened
Certain recommended modifications not completed

## Slide 7: Tropical Storm Sandy - 2012
  Category 2 Hurricane downgraded to a post-tropical cyclone. High winds and storm surge.

## Slide 8: Tropical Storm Sandy Damage
Impact to the Pavilion
  Existing spread footings performed poorly
  Loss of beach
  Sand behind bulkhead liquefied
  Sands surrounding and under footings eroded/scoured
  Existing bulkhead opening provided a convenient channel for sand transport and funneled flood waters – increasing velocity

## Slide 9: Tropical Storm Sandy Damage
  Impact to the Pavilion
    Foundation settlement
    Structural damage
    Damaged building systems and finishes
    Building deemed unsafe by Town Building officials

## Slide 10: Post Sandy Investigations and Reports
Structural engineer inspection of storm damage – footings, structure and interior.
Mechanical, electrical and plumbing systems not inspected.
Coastal engineer study of impacts of coastal storms.
Geotechnical study, soil borings (testing) and report.
Repair scope of work and cost estimating.
Additional soil borings adjacent to and under building.
Structural re inspection fall 2014

## Slide 11: 2014 Site Protection
Committee approved additional protection and make-safe safety measures:
  Additional security fencing
  Inspection of gas and electrical systems
  Installed alarm/security system
  Temporary Removal of Gathering Hall Glass
    In storage for reuse
  Permanent closure of openings in bulkhead

## Slide 12
Original Penfield Phase I and Phase II construction documents
Investigative engineering reports (Irene and Sandy)
  JM Albaine Engineering
  Roberge Associates Coastal Engineers
  Heller and Johnsen Geotechnical Engineers
Storm damage insurance claim, repair, scope and cost estimates
  Wakelee Associates
  Romano Construction
  Saugatuck Construction Group
Engineer, Architect and Construction Manager interviews
  Competitive interview and selection April/May 2013
  DeStefano & Chamberlain and Shawmut Design & Construction selected
Public input
PBC – Research and Due Diligence

## Slide 13
Presentations before the Committee:
  JM Albaine Engineering (including results of 8/2013 Public Forum)
  Roberge Associates Coastal Engineers
  Heller and Johnsen Geotechnical Engineers
  Fairfield DPW and Engineering Departments
  Building Department
  Conservation Department
  Parks and Recreation Director
  Town Plan and Zoning (including FEMA/Flood Zone requirements)
  Town Risk Manager (insurance settlement)
  Flood and Erosion Control Board
  Report regarding additional soil borings
PBC – Research and Due Diligence

## Slide 14
Extent of foundation damage | Beach accretion and loss
Cause of damage/Contributing factors | Existing timber bulkhead location/performance
Feasibility of Repairs | Facility /site impact on neighborhood flooding
Existing site soil conditions | Constructability and project safety
Footing depths | Building height and mass – impact on neighborhood
Alternate foundation designs and soil bearing quality/capacity | Project Cost
Coastal Storm Impacts – past and future | Cost recovery funding resources
Coastal Storm protection | Insurance Claims
FEMA Flood Zone Requirements | Schedule
FEMA Reimbursement Rules | Chief Fiscal Officer Financial Summary
PBC – Factors Considered

## Slide 15: Repair Options
PBC reviewed 11 repair options to varying degrees
    8 options were reviewed during the 8/14 Committee meeting
    3 options were added after the 8/14 meeting (two in response to public comment)
5 repair options given final consideration
    Repair & Protect (Option 1)
    Complete Demolition & Site Reconstruction (Option 8)
    Demolition & Construct Smaller Facility (Option 9)
    Modify & Raise Building (Option 7)*
    Modify & Raise Building and Reconstruct East Wing (Option 7A)
* The Committee originally approved Option 7. Option 7A was subsequently approved after financial information based on FEMA rules were provided by the Chief Fiscal Officer and endorsement given by the Parks and Recreation Department.

## Slide 16: Background
Pavilion Appraised Value: $5,400,000 (determined during insurance settlement)
Current FEMA requirements must be followed if the value of the repair is greater then 50% of the appraised value of the building.
  Pavilion actual construction cost would need to be no greater than $2,650,000
Coastal and Structural Engineering Recommendation: the building should be re-supported on a new flood-resistant pile foundation system

## Slide 17: Background (cont’d)

## Slide 18: Background (cont’d)
Site FEMA Flood Zone changed from an A zone (moderate wave action) to a V zone (high velocity wave action)
  Original construction was FEMA AE Zone
  AE zone: Base Flood Elevation (BFE) of 11.0’ finish floor
  V zone: Base Flood Elevation (BFE) of 13.0’
    (Note: measured to lowest horizontal structural element)

## Slide 19: Background (cont’d)

## Slide 20: Option 7A Repair and Reconstruct Committee Recommended Approach
Demolish the East Wing and exterior decks
    Not financially practical to move – tear off and reconstruct
Lift/move the West Wing building into the parking lot
Repair structural and non-structural damage
Construct new pile supported foundations for East and West Wings
New steel elements supporting floor structure
Redesign and reconstruct East Wing
Create a new, continuous berm connecting Durrell Pavilion to Rickards Beach

## Slide 21: Option 7A Repair and Reconstruct Committee Recommended Approach (cont’d)
Move West Wing back in place, 3.5’ higher in elevation
Repair any remaining damage
Fill beneath and around the building
Construct on grade decking, new stairs and ramps
Finished elevation of the site will be +12’
Estimated total project cost: $6,028,709

## Slide 22: Partial Demolition
Existing Locker Wing, decks and stairs to be Demolished
Remove Existing Elevated Decks, Ramps and Stairs. Roofs To Remain

## Slide 23: Move Building
Temporary building location

## Slide 24
Cut back existing floor joists
Remove existing dropped wood beams
Install galvanized steel beams with wood blocking
Install galvanized steel stub column down to concrete pier
Pier
Grade beam
Timber pile
Install Foundations

## Slide 25
Infill ALL openings in accordance with original design
Riprap stone revetment on Long Island side of bulkhead
Bulkhead Improvements

## Slide 26
Option 7A – Floor Plan

## Slide 27
Option 7A – Elevations

## Slide 28
Option 7A – Sections

## Slide 29
Option 7A – Renderings
View from the Southeast
View from the Southwest

## Slide 30
View from the Northwest
Option 7A – Renderings